## Defects
Customer | Project key | Project name | Project type | Summary | Description | Issue Type | Project lead | Priority | Assignee Email | Reporter Email | AssignApprovalStatus | AttachmentPaths | JiraTicketID | ExecutionStatus | ProcessedAt | DuplicateOccurrenceCount | ReassignedToEmail | ReassignStatus
Orica | JAIT | Jira Automate Ignite Testing | software | ABAP dump ASSIGN_CASTING_ILLEGAL_CAST in ZCL_CC_FIELD_MAPPER=>MAP_STRUCTURE | Runtime error ASSIGN_CASTING_ILLEGAL_CAST when assigning ls_vbap to field-symbol <ls_target> typed with the new CDS structure. Field lengths differ after Table-to-CDS conversion (MATNR 18 -> 40). | Bug | Medisetty Karthik | High Attention | mkarthik@smartshift.com | mkarthik@smartshift.com | Approved | attachments/samples/st22_cast_dump.png¦attachments/samples/analysis_cast_error.docx | JAIT-12 | PROCESSED | 2026-10-29T08:14:51.014Z | 2 |  | None
Orica | JAIT | Jira Automate Ignite Testing | software | CDS view ZI_SalesDocItem returns duplicate rows after VBAP replacement | After replacing direct SELECT on VBAP with CDS view ZI_SalesDocItem the item count doubles for orders with multiple schedule lines (VBEP). Join cardinality on _ScheduleLine is MANY instead of ONE. | Bug | Medisetty Karthik | High | mkarthik@smartshift.com | mkarthik@smartshift.com | Approved | attachments/samples/cds_duplicate_rows.png¦attachments/samples/cds_row_counts.xlsx | JAIT-16 | PROCESSED | 2026-10-30T07:10:18.608Z | 2 | asarath@smartshift.com | Approved
P&G | JAIT | Jira Automate Ignite Testing | software | CFL: custom field ZZ_BATCH_ORIGIN not propagated from goods receipt to MATDOC | Field created in Custom Fields app for Material Document Item. Value is entered via Post Goods Receipt but MATDOC.ZZ_BATCH_ORIGIN stays initial. Check propagation for the business context. | Task | Medisetty Karthik | Medium | mkarthik@smartshift.com | mkarthik@smartshift.com | Approved | attachments/samples/cfl_field_missing.png¦attachments/samples/cfl_propagation_notes.docx¦attachments/samples/mrp_type_comparison.xlsx | JAIT-13 | PROCESSED | 2026-10-29T08:38:18.595Z | 2 | knsspreddy@smartshift.com | Approved
P&G | JAIT | Jira Automate Ignite Testing | software | AMF syntax failure: missing period after DEFINE ROLE in ZAMF_AUTH_SALES | Activation fails: 'The statement DEFINE ROLE must end with a period' at line 17 of ZAMF_AUTH_SALES. Introduced by the automated formatter in ADT. | Bug | Medisetty Karthik | Low | mkarthik@smartshift.com | mkarthik@smartshift.com | Approved | attachments/samples/st22_cast_dump.png¦https://docs.github.com/en/rest/repos/contents | JAIT-17 | PROCESSED | 2026-10-30T07:45:05.433Z | 2 |  | None
VOITH | JAIT | Jira Automate Ignite Testing | software | Table-to-CDS: MARA/MARC join replaced by I_Product loses plant-specific MRP type | ZMM_MRP_OVERVIEW previously joined MARA and MARC. After moving to CDS I_Product with association _ProductPlant the MRP type (DISMM) is blank for plants 1010 and 1020. | Story | Medisetty Karthik | Medium | mkarthik@smartshift.com | mkarthik@smartshift.com | In Progress | attachments/samples/mrp_type_comparison.xlsx¦attachments/samples/analysis_cast_error.docx |  | PENDING |  | 2 |  | None
Note on A1: REFERENCE ONLY. Shown on the dashboard, never sent to Jira.
Note on B1: Jira space (project) key, e.g. JAIT. Required. Optional aliasing via JIRA_PROJECT_MAP.
Note on C1: Reference only (e.g. Jira Automate Ignite Testing). Not sent to Jira.
Note on D1: Reference only (e.g. software). Not sent to Jira.
Note on E1: Short ticket title (max 255 chars). Required.
Note on F1: Full defect description incl. dump text / object names. Required.
Note on G1: Must exist in the Jira space, e.g. Bug, Task, Story, Epic. Required.
Note on H1: Free text; added to the ticket description header (or a custom field via JIRA_LEAD_FIELD).
Note on I1: Must match a priority name in your Jira, e.g. High Attention, Medium, Low. Required.
Note on J1: Jira user's email OR display name. Required.
Note on K1: Jira user's email OR display name. Required.
Note on L1: System managed. Leave 'In Progress'.
Note on M1: Pipe-separated. Each entry = file name uploaded with this file, a path on the server, or an https:// link. e.g. error.png¦analysis.docx¦https://...
Note on N1: System managed. Auto-populated on approval.
Note on O1: System managed: PENDING / PROCESSED / FAILED.
Note on P1: System managed ISO timestamp.
Note on Q1: System managed. +1 per suppressed duplicate.
Note on R1: System managed. Set by Change Assignee.
Note on S1: System managed: None / In Progress / Approved.

## Attachments
JiraTicketID | Summary | File / link | Type | Status | Open (GitHub or link)
JAIT-12 | ABAP dump ASSIGN_CASTING_ILLEGAL_CAST in ZCL_CC_FIELD_MAPPER=>MAP_STRUCTURE | st22_cast_dump.png | image | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/st22_cast_dump.png
JAIT-12 | ABAP dump ASSIGN_CASTING_ILLEGAL_CAST in ZCL_CC_FIELD_MAPPER=>MAP_STRUCTURE | analysis_cast_error.docx | word | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/analysis_cast_error.docx
JAIT-16 | CDS view ZI_SalesDocItem returns duplicate rows after VBAP replacement | cds_duplicate_rows.png | image | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/cds_duplicate_rows.png
JAIT-16 | CDS view ZI_SalesDocItem returns duplicate rows after VBAP replacement | cds_row_counts.xlsx | excel | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/cds_row_counts.xlsx
JAIT-13 | CFL: custom field ZZ_BATCH_ORIGIN not propagated from goods receipt to MATDOC | cfl_field_missing.png | image | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/cfl_field_missing.png
JAIT-13 | CFL: custom field ZZ_BATCH_ORIGIN not propagated from goods receipt to MATDOC | cfl_propagation_notes.docx | word | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/cfl_propagation_notes.docx
JAIT-13 | CFL: custom field ZZ_BATCH_ORIGIN not propagated from goods receipt to MATDOC | mrp_type_comparison.xlsx | excel | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/mrp_type_comparison.xlsx
JAIT-17 | AMF syntax failure: missing period after DEFINE ROLE in ZAMF_AUTH_SALES | st22_cast_dump.png | image | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/st22_cast_dump.png
JAIT-17 | AMF syntax failure: missing period after DEFINE ROLE in ZAMF_AUTH_SALES | contents | link | stored | https://docs.github.com/en/rest/repos/contents
| Table-to-CDS: MARA/MARC join replaced by I_Product loses plant-specific MRP type | mrp_type_comparison.xlsx | excel | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/mrp_type_comparison.xlsx
| Table-to-CDS: MARA/MARC join replaced by I_Product loses plant-specific MRP type | analysis_cast_error.docx | word | stored | https://github.com/mkarthik-sst/smartshift-defect-hub/blob/main/attachments/c47f3a51-aebe-47e7-8b8b-fc3a4b026a64/analysis_cast_error.docx

## Ingestion Log
Item | Row | Detail
File |  | CleanCore_Defects_SAMPLE (3).xlsx (immediate) at 2026-10-29T07:07:43.786Z
Rows read / staged / duplicates / invalid |  | 5 / 5 / 0 / 0